## Product Backlog
Constructor | Story | Justification of Ticket | Completion Requirement | Summary | Component | Assignee | Assigned | Estimated Time (days) | Status | Sprint
Backend and Frontend | As a developer, I would like to be able to use Semantic UI | React allows for a very clean and nice looking frontend and would make it easier to develop | The UI is very easy to use and allows users a simple navigation of the website | REACT and Django | Frontend |  | Nathan | 2 |  | 1
Backend | As a listener, I would like to see the most recently viewed streams | The Home Page needs to show the users most current DJ's, favorite DJs, and most Popular DJs right now | Home Page has at least 2 of the specified aspects of the home page | Home Page should have suggested DJs | Home Page |  | Josh | 2 |  | 1 | html done in sprint 1
Backend | As a listener, I would like to have a profile with a list of DJ's that I'm following | Allow listeners to easily know who they listen to | Profile has a list of DJ's following | User's have individual profile. They follow Stream | Profile |  | Tony | 0.5 |  | 1
Backend | As a listener, I would like to be able to select DJ's to follow and unfollow | This allows listeners to easily find their DJ's that are currently streaming | There exists a working follow button and follower value | Following | Profile |  | Tony | 0.5 |  | 1
Spotify API | As a DJ, I would like to be able to access my Spotify account in order to monitor and play songs to start a radio | In order to allow for global access to queues we need to understand how the spotify api interacts with django. | DJ can add a song to a new playlist, or a song can be added to the playback queue | DJ adds song to Stream | Spotify |  | Nathan/Tony | 3 |  | 1
Spotfiy API | As a Spotify Developer, I need to create a playlist | Within Spotify Queues can only start working after some music has been played. | A playlist is created or reused when starting DJ session | Create a default playlist for new Queue | Spotify |  | Krish | 1 |  | 1
Spotify API | As a DJ, I would like to merge my account with spotify so I can stream my songs | This allows the DJ to push songs onto their playback queue | Songshare account can link to spotify | Link Accounts | Spotify |  | Krish | 2 |  | 1 |  | 13
Frontend | As a developer, I would like have a frontend | We need a front end for our code to work | Basic front end | HTML | UI |  | Josh | 1 |  | 1
Spotify API | As a listener or a DJ, I would like to be able to search for songs | This allows listeners and djs to add songs to a stream | Listener/DJ is able to look up songs to add to streams | Listeners search for songs | Search |  | Tony | 3 |  | 2
Database | As a developer, I would like my website to be housed on the cloud and accessible to all | Storing information is required the a database and we would like the server to be accessible to all | Using AWS we should be able to store information regarding profiles and streams online | Database | Database |  |  | 1 |  | 2
Frontend and Backend | As a listener, I would like to know when a DJ is live | In order for users to access streams they must be able to see which streams have an administrator. | Visual queue when a DJ is live | Live DJ | DJ |  |  | 3 |  | 2 | Could take more or less time
Backend | As a DJ, I want to monitor the songs that are added to my stream and have the option to remove songs from stream | DJ's may choose to moderate their stream and song selection | DJ is able to remove requested songs to add to stream. This can be done through Spotify api or managing the stream on song share | DJ Moderation | DJ |  |  | 1 |  | 2
Backend | As a DJ, I would like to move songs up and down on the stream | In order to monitor songs, a DJ might want to be able to move songs up and down the queue | DJ can drag songs up and down the queue | Stream interface | DJ |  |  | 2 |  | 2
Spotify API and Backend | As a listener, I would like to be able to add songs to the stream | In order for users to request the songs they need to be able to select queues and songs they would like to add | User can add songs to DJ's playlist or stream | Listeners add songs to playback queue | Listener |  |  | 5 |  | 2 | Concurrency issues exist
Backend | As a listener, I would like to be able to search DJs by name | This allows listeners to find different DJs and select the ones they want to follow | Listener can look up DJ's both live and not live | Listeners search for DJs | Search |  |  | 2 |  | 2
Backend | As a listener, I would like to see search results close to my request | In order to make it easier for listeners to find the DJ's we need to display suggested values | Suggested DJ's appear on slightly incorrect search | Suggested DJs | Search |  |  | 2 |  | 2 | This might not be feasible. However, a possible algorithm could be: if (no DJ matches search term) then return all DJs ordered by the Levenshtein distance between the name and the search term
Frontend | As a developer, I would like by website to have a nice UI | Our website must be visually appealing and easy to use. | Beautified front end | HTML/CSS | UI |  |  | 2 |  | 2
Backend | As a listener, I would like to vote on the songs on the stream | This allows DJs to gain feedback from their listeners on what they want to hear | The voting system is implemented in the project | Voting | DJ |  |  | 3 |  | 2

## Sprint #1 Backlog
Constructor | Story | Justification of Ticket | Completion Requirement | Summary | Component | Assignee | Assigned | Estimated Time (days) | Status
Backend and Frontend | As a developer, I would like to be able to use Semantic UI | React allows for a very clean and nice looking frontend and would make it easier to develop | The UI is very easy to use and allows users a simple navigation of the website | REACT and Django | Frontend |  | Nathan | 2
Backend | As a listener, I would like to see the most recently viewed streams | The Home Page needs to show the users most current DJ's, favorite DJs, and most Popular DJs right now | Home Page has at least 2 of the specified aspects of the home page | Home Page should have suggested DJs | Home Page |  | Josh | 2
Backend | As a listener, I would like to have a profile with a list of DJ's that I'm following | Allow listeners to easily know who they listen to | Profile has a list of DJ's following | User's have individual profile. They follow Stream | Profile |  | Tony | 0.5
Backend | As a listener, I would like to be able to select DJ's to follow and unfollow | This allows listeners to easily find their DJ's that are currently streaming | There exists a working follow button and follower value | Following | Profile |  | Tony | 0.5
Spotify API | As a DJ, I would like to be able to access my Spotify account in order to monitor and play songs to start a radio | In order to allow for global access to queues we need to understand how the spotify api interacts with django. | DJ can add a song to a new playlist, or a song can be added to the playback queue | DJ adds song to Stream | Spotify |  | Nathan/Tony | 3
Spotfiy API | As a Spotify Developer, I need to create a playlist | Within Spotify Queues can only start working after some music has been played. | A playlist is created or reused when starting DJ session | Create a default playlist for new Queue | Spotify |  | Krish | 1
Spotify API | As a DJ, I would like to merge my account with spotify so I can stream my songs | This allows the DJ to push songs onto their playback queue | Songshare account can link to spotify | Link Accounts | Spotify |  | Krish | 2
Frontend | As a developer, I would like have a frontend | We need a front end for our code to work | Basic front end | HTML | UI |  | Josh | 1